## Sheet1
TimeFrame	Item	Description	Comment	Alpha	Beta	RC	Final
7 Days Before Alpha	Bug Hunting	Announce on mailing lists (dev, qa, project, user)	We'll need to figure out a solid date (thinking RC1 release date lasting 7 days). Also we would want to somehow highlight/train people to look the hardest for regressions and to prioritize really terrible ones high so that they are fixed before release)
7 Days Before Alpha	Bug Hunting	Contact marketing/website teams to get a banner up on our site	Would be nice to have a contact for this
Alpha Release Date	Bug Hunting	Make sure banner is up and looks pretty
Alpha Release Date	Testing	Install and make sure major features work	Would be nice to have a way to track this, also would want to make a list of features to check (wizards, printing, running each component, etc . . .)
Alpha Release Date	Testing	Moztrap	Begin moztrap testing
Beta1 Release Date	Bug Hunting	Announce on mailing lists (dev, qa, project, user)	Announce for a second time, repetition seems to work well. Also might want to get a list of anyone who has done it in the past and BCC or CC them on it so they get an individual notice
Beta1 Release Date	Testing	Install and make sure major features work	Same as Alpha1
Beta1 Release Date	Testing	Continue testing moztrap	We need to collectively take some time to learn this I think – we're all pretty up to par on bibisect but moztrap seems to be this black hole for many people. Perhaps a training session for us from Sophi would be good?
Beta 2 Release Date	Testing	Install and make sure major features work	Same as Alpha1
Beta 2 Release Date	Testing	Moztrap	Finish moztrap testing
RC1 Release Date	Bug Hunting	Announce on mailing lists (dev, qa, project, user)	It has started! Yay! Make sure we have IRC coverage
RC1 Release Date	Testing	Install and make sure major features work	Same as Alpha1
7 Days After RC1	Bug Hunting	Finish off the bug hunting session	QA team start reviewing any bugs reported in that time frame – check for critical bugs that we can try to get fixed before release
RC2	Testing	Install and make sure major features work	Same as Alpha1
Final Release	Testing	Install and make sure major features work	Same as Alpha1
Final Release	Bug Hunting	Redirect banner to a thank you page for those who participated Announce top participants	Prizes would be nice but the shipping thing is such an insane mess that not sure if it's practical